## Getting the Environment Ready
Getting the Environment Ready |  | S4X | S4D | S4Q | S4P
1 | Download & install CIG AddOn software components: | Completed | Completed | Completed | Completed
2 | Enable CIG: | Completed | Completed | Completed | Completed
3 | Download, install & configure SAP Cloud Connector | Completed | Completed | Completed
4 | Define Global Settings: | Completed
5 | Send SAP system information to CIG:
6 | Start creating an Integration Project in CIG Portal:

## Configure the Solution
Configure the Solution
1 | Maintain General Settings:
2 | Import Master Data:
3 | Configure Transactions:
4 | Specify Cross-Reference Values in CIG Integration Project:
5 | Implement extensions and BADIs:
6 | Map custom fields with CIG's Mapping Tool:

## Review & Deploy
Review & Deploy
1 | Review CIG project configuration:
2 | Testing
3 | Deployment: