## Business Network
Type | Task Description | Additional Information/Task Completion Notes | Status | WS (Team) | Location/Plant | Start Date | Start Time (EDT) | Predecessor | Duration | End Date | End Time (EDT) | Accountable | Responsible | Task Type | Sub-Task Type
| Download & install CIG AddOn software components | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Enable CIG | 2 weeks before cutover - System Business Network Ariba - CIG | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Configure SAP Cloud Connector | Precutover - Advansix Cloud Connector | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Define Global Settings | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Start creating an Integration Project in CIG Portal | 2 weeks before cutover - System Business Network Ariba - CIG | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Maintain General Settings | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Configure Transaction - Purchase Order | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Configure Transaction - Purchase Order Confirmation | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Configure Transaction - Invoice | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Configure Transaction - Ship Notice/ASN | Precutover - System S4P | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Specify Cross-Reference Values in CIG Integration Project | 2 weeks before cutover - System Business Network Ariba - CIG | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Testing - Outbound and Inbound Connection | 2 weeks before cutover - System Business Network Ariba - CIG | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju
| Deployment | Cutover | 10 - NEW |  | N/A | [6 empty] | Jim Burrows | Shamala Thimmraju